## Slide 1: WELCOME Batch-26
Farhana Sultana Naima
Roll No : 01-026-25

## Slide 2: Date : 23/09/24
What i have done today?
1.Project name done
2.Questionere done
What will I do tomorrow?
1.Read more relatable paper
What problem I faced?
1.difficulties on data collection

## Slide 3: Date : 26/09/24
What i have done today?
1. Read more relatable paper
gain basic knowledge on this paper.
What will I do tomorrow?
1.Complete Literature Review
2.Data Analysis
3.Draft Sections

## Slide 4: Date : 29/09/24
What i have done today?
1.Completed Literature Review
Finalized reading key articles on remittance impact.
2.Data Analysis
Analyzed survey data using statistical software.
3.Drafted Sections
Wrote initial draft for the methodology section.
What will I do tomorrow?
1. Finalize Data Analysis
2. Continue Writing

## Slide 5: Date : 01/10/24
What i have done today?
1.Finalize Data Analysis
Interpret results and prepare visualizations. Surveys from 113 respondents.
2.Continue Writing
Work on the findings section.
What will I do tomorrow?
1.Write Literature Review
2.Complete Findings Section

## Slide 6: Date : 02/10/24
What i have done today?
1.Write Literature Review
2.Completed Findings Section
Summarize key results.
What will I do tomorrow?
1.Statistical Methods
2.Thesis Writing
What problem I faced?
1.Data Collection Delays
Some responses were late

## Slide 7: Date : 03/10/24
What i have done today?
1.Completed Statistical Methods
2.Starting Thesis Writing
What will I do tomorrow?
1.Data Analysis
2.Drafting Full Thesis

## Slide 8: Date : 04/10/24
What i have done today?
1.Finalized data Analysis
2.Drafted Full Thesis & findings
3. Completed Citation & Referance
What will I do tomorrow?
1.Submit project paper

## Slide 9: Date : 05/10/24
Submitted
THANK YOU